## README
R5B AMP KITTING — RELEASE LOG ARCHIVE (STATIC)
Created 05-Oct-2026 when the operational workbook moved to manually maintained cumulative totals (R5B-AMP-Kitting-Control-v2.xlsx).
This file is history only. Nothing in the operational workbook links to it. Do not add new rows here.
Sheet 'Release Log (archive)': the 182 lines exactly as recorded in the previous workbook's Release Log sheet (Date, Contract, Assy Code, Qty Released, Released By, Note, Description). They were built from the COOIS export new_e2a (run 03-Oct-2026) and cover E2A-R12P-T5-C repeaters 1–13. 'Released By' was blank in the original. The original 'Check' column was a formula with no recorded value and is not reproduced.
Sheet 'Migration reconciliation': per contract + assembly code, the previous workbook's released total, the sum of the archived log lines, and the opening cumulative supplied total in the new workbook. All 30 rows match.
Sheet 'Contracts & plan check': contract settings and scheduled totals before/after migration. All 12 contracts and all 146 plan rows are identical.
Keep full SAP exports (COOIS / CO41 / ZMRP) in the company SAP-export folder, not in either workbook.

## Release Log (archive)
Date | Contract | Assy Code | Qty Released | Released By | Note (WO / repeater) | Description
2026-04-20 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 1 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-05-06 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 1 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-05-06 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 1 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-05-06 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 1 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-05-14 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 1 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-05-14 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 1 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-05-14 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-05-16 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-05-18 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-05-18 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 2 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-05-18 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 2 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-05-19 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 2 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-05-20 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 2 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-05-21 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 2 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-05-21 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 2 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-05-23 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-05-23 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-05-23 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-05-28 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 3 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-05-28 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 3 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-05-29 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 3 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-06-03 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 1 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-06-03 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-06-03 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-06-03 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-06-04 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-06-05 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-06-07 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 2 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-06-09 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 3 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-06-09 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 3 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-06-09 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 3 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-06-15 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 4 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-07-20 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 3 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-07-21 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 4 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-07-22 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 5 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-07-23 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-07-23 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-07-23 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-07-23 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-07-28 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 4 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-07-28 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 4 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-07-29 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-07-31 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 4 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-07-31 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 4 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-08-04 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 4 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-08-04 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 5 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-08-04 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 5 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-08-07 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-08-07 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-08-07 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-08-09 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 5 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-08-09 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 6 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-08-09 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 6 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-08-10 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 5 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-08-10 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 5 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-08-10 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 6 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-08-12 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 5 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-08-12 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-08-12 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-08-12 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-08-12 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-08-17 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 6 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-08-17 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 7 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-08-19 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 7 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-08-22 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 6 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-08-22 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 6 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-08-22 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 6 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-08-22 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 7 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-08-25 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 8 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-08-27 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-08-27 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-08-27 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-08-27 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-09-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 7 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-09-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 7 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-09-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 8 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-09-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 8 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-09-04 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 7 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-09-04 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-09-04 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-09-04 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-09-04 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-09-07 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 7 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 9 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 10 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 11 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-09-09 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-09-10 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 8 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-09-11 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 8 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-09-11 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 9 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-09-11 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 12 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-09-11 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 13 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP
2026-09-13 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 8 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-09-13 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 8 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-09-13 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 9 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-09-16 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-09-16 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-09-16 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-09-16 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-09-21 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 9 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-09-21 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 10 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-09-22 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 9 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-09-22 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 9 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-09-22 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 10 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-09-28 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 9 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-09-28 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-09-28 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-09-28 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-09-28 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 10 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 10 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 10 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-10-01 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 10 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-10-01 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-10-01 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-10-01 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 11 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 11 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 11 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 11 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 11 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-10-01 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 11 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-10-01 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-10-01 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-10-01 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-10-01 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 12 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 12 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-10-01 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 12 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 12 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 12 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-10-02 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 12 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-10-02 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-10-02 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-10-02 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 13 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 13 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 13 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 13 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A
2026-10-02 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 13 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A
2026-10-02 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 13 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A
2026-10-02 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1
2026-10-02 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2
2026-10-02 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3
2026-10-02 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP)
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP)
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP)

## Migration reconciliation
Contract | Assembly code | Qty per repeater (old) | Qty per repeater (new) | Released total (old workbook) | Sum of archived log lines | Opening cumulative supplied (new) | Complete sets (old) | Complete sets (new) | Match
E2A-R12P-T5-C | 92YLS00548BAA | 1 | 1 | 13 | 13 | 13 | 13 | 13 | YES
E2A-R12P-T5-C | 92YLS00548BBA | 2 | 2 | 26 | 26 | 26 | 13 | 13 | YES
E2A-R12P-T5-C | 91YAF03404AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92YFD04548BAA | 1 | 1 | 13 | 13 | 13 | 13 | 13 | YES
E2A-R12P-T5-C | 92YFD04548BBA | 2 | 2 | 26 | 26 | 26 | 13 | 13 | YES
E2A-R12P-T5-C | 92YWS04548AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92RRA00548AAA | 24 | 24 | 312 | 312 | 312 | 13 | 13 | YES
E2A-R12P-T5-C | 92YRA01548AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92YRA02548AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92YRA03548AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92YRA04548AAA | 3 | 3 | 39 | 39 | 39 | 13 | 13 | YES
E2A-R12P-T5-C | 92UAP04548BAA | 1 | 1 | 13 | 13 | 13 | 13 | 13 | YES
E2A-R12P-T5-C | 92UAP04548BBA | 1 | 1 | 13 | 13 | 13 | 13 | 13 | YES
E2A-R12P-T5-C | 92UAP04548BCA | 1 | 1 | 13 | 13 | 13 | 13 | 13 | YES
WKE-R24P-T1-C | 92YLS00543AAA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YLS00543ABA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YLS00543ACA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 91YAF03404AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YFD44543AAA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YFD44543ABA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YFD44543ACA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YWS04543AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YRA01543AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YRA02543AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YRA03543AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92YRA04543AAA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92RRA00543AAA | 48 | 48 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92UAP44543AAA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92UAP44543ABA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES
WKE-R24P-T1-C | 92UAP44543ACA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | YES

## Contracts & plan check
Contract | Settings identical (top code, amps/rep, total, kit lead; AMPS lead = 1) | Scheduled total (new = old) | Plan rows identical (all contracts)
WKE-R24P-T1-C | YES | 255 | YES
WBA-R24P-T1-C | YES | 200 | YES
E2A-R4P-T1-C | YES | 39 | YES
E2A-R4P-T2-M | YES | 11 | YES
E2A-R6P-T3-M | YES | 3 | YES
E2A-R8P-T4-C | YES | 10 | YES
E2A-R12P-T5-C | YES | 126 | YES
E2A-R12P-T6-C | YES | 5 | YES
E2A-R16P-T7-C | YES | 9 | YES
DARAJA-R8P (TBC) | YES | 10 | YES
DARAJA-R24P (TBC) | YES | 46 | YES
REUNION-SOUTH-R16P (TBC) | YES | 31 | YES