## Dashboard
R5B E2A 12FP COLD T5 KITTING CONTROL · WK 40 | [9 empty] | VIEW REPEATER ▸ | All | Required = release qty
Contract R5B · E2A 12FP Cold T5 · 92ERP12548A++ · 12FP · Repeaters 1-13 · 1 to release | [10 empty] | Pick All or 1–13
ASSEMBLIES |  | REQUIRED QTY | WO COVERAGE |  |  | WORK ORDERS |  | SHORT / OVER |  | DATA FLAGS
14 |  | 51 | 0% |  |  | 0 |  | 0 |  | 0
6 sequences · 0 fully covered |  | units · release across 1 repeater | 0 of 51 units on WOs |  |  | 0 closed · 14 codes with no WO |  | 0 short · 0 over |  | 0 plan qty checks · 0 WO entry flags
COVERAGE BY SEQUENCE | [6 empty] | WORK-ORDER PIPELINE
Sequence | Codes | Coverage | Required | WO Qty | % |  | Status | WOs | Qty | Share of WOs
LASER ASSY | 2 | 0 | 3 | 0 | 0% |  | Planned | 0 | 0 | 0%
PSB ASSY | 1 | 0 | 3 | 0 | 0% |  | Released | 0 | 0 | 0%
OPF ASSY | 2 | 0 | 3 | 0 | 0% |  | Kitted | 0 | 0 | 0%
POB ASSY | 1 | 0 | 3 | 0 | 0% |  | Closed | 0 | 0 | 0%
ERBIUM ASSY | 5 | 0 | 36 | 0 | 0% |  | Total | 0 | 0
BOAT ASSY | 3 | 0 | 3 | 0 | 0% |  | ✓ Every release qty = default qty × repeaters
ASSEMBLY LEDGER |  | Coverage = WO qty ÷ required qty for the selected view. Repeater views count each 'All' WO split evenly across the repeaters being released.
Sequence | Assy Code | Description | Release | Default / Rep | Required | WO Qty | Coverage | Status | WOs | Closed Qty | Work Order Nos. | Plan Check
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 1 | 1 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 2 | 2 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 1 | 1 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 2 | 2 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 24 | 24 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 3 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 1 | 1 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 1 | 1 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 1 | 1 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0

## Kitting Plan
KITTING PLAN — MASTER DATA
Source: kitting plan table supplied by the user (R5B · E2A 12FP Cold T5 · 92ERP12548A++ · 12FP · WK 40). Blue cells are inputs; edit them when the plan changes.
Contract | Sequence | Assy Code | Assy Description | Release | Repeater No. | No. of Rep to Rel | Default Qty | Check
R5B | LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 1-13 | 1 | 1 | OK
R5B | LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 1-13 | 1 | 2 | OK
R5B | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 1-13 | 1 | 3 | OK
R5B | OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 1-13 | 1 | 1 | OK
R5B | OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 1-13 | 1 | 2 | OK
R5B | POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 1-13 | 1 | 3 | OK
R5B | ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 1-13 | 1 | 24 | OK
R5B | ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 1-13 | 1 | 3 | OK
R5B | ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 1-13 | 1 | 3 | OK
R5B | ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 1-13 | 1 | 3 | OK
R5B | ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 1-13 | 1 | 3 | OK
R5B | BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 1-13 | 1 | 1 | OK
R5B | BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 1-13 | 1 | 1 | OK
R5B | BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 1-13 | 1 | 1 | OK
Contract details shown on the Dashboard
Contract | R5B
Program | E2A 12FP Cold T5
ERP item | 92ERP12548A++
Config | 12FP
Kitting week | WK 40
Repeaters | 1-13 · 1 to release

## Work Orders
WORK ORDERS
Type the WO number and pick the assy code. Quantity fills in automatically from the kitting plan (release qty, or default qty when a single repeater is chosen).
Blue columns = you type. Grey columns = automatic. Use 'Qty Override' only when the WO quantity differs from the plan.
|  |  |  | Blank = All |  | Leave blank to use Listed Qty |  | Blank = Planned
WO No. | Assy Code | Description | Sequence | Repeater | Listed Qty | Qty Override | WO Qty | Status | Release Date | Remarks | Flag

## Lists (hidden)
92YLS00548BAA
92YLS00548BBA
91YAF03404AAA
92YFD04548BAA
92YFD04548BBA
92YWS04548AAA
92RRA00548AAA
92YRA01548AAA
92YRA02548AAA
92YRA03548AAA
92YRA04548AAA
92UAP04548BAA
92UAP04548BBA
92UAP04548BCA

## How To Use
HOW TO USE THIS WORKBOOK
For the team
1. Add a work order | Go to 'Work Orders'. Type the WO number in column A and pick the assy code in column B. Description, sequence and quantity fill in by themselves.
2. Quantity | WO Qty = the listed qty from the kitting plan (e.g. 24 for 92RRA00548AAA, 2 for 92YLS00548BBA). Pick the repeater (1–13) the WO belongs to, or leave it blank for the repeater being released. Type in 'Qty Override' only if the WO is for a different quantity.
3. Update status | Change 'Status' as the WO moves: Planned → Released → Kitted → Closed. Blank counts as Planned.
Example entry | WO No. = WO-4012871 · Assy Code = 92YLS00548BAA · Repeater = 5 · Qty Override = (blank) · Status = Released
Flags | Column L on 'Work Orders' warns about duplicate WO numbers, missing codes or codes not in the plan.
For management
Dashboard | Shows the whole plan on one screen: totals at the top, coverage by sequence, the WO pipeline, and every assembly with its WOs.
Read the Status column | NO WO = nothing raised yet · SHORT n = WOs cover less than required (n units missing) · COVERED = WO qty matches · OVER = more WO qty than required.
Trace a WO | The 'Work Order Nos.' column lists every WO on each assy code. To go the other way, filter column A on 'Work Orders'.
Switch repeater view | Pick All or a repeater number 1–13 in the pink cell at the top right of the Dashboard. 'All' checks every WO against the release qty; a number shows only that repeater's WOs (plus WOs left blank/All).
Projecting on a screen | Open the Dashboard tab and press Ctrl+F1 to hide the ribbon. The dashboard fits one landscape screen; adjust zoom to your projector if needed. Excel recalculates as soon as anyone adds a WO.
Live sharing | Save the file on SharePoint / OneDrive / Teams so several people can edit while the dashboard is on screen.
Changing the plan | Edit the blue cells on 'Kitting Plan' (codes, release qty, default qty). The Dashboard and WO lookups follow automatically.