## Dashboard
187
R5B E2A 12FP COLD T5 · REPEATER COUNTER | [6 empty] | REPEATERS REQUESTED ▸ | 13
Contract R5B · E2A 12FP Cold T5 · 92ERP12548A++ · 12FP · Contract: 13 repeaters · 182 releases logged | [7 empty] | type the target here
REPEATERS KITTED |  | REQUEST STATUS | UNITS TO RELEASE |  |  | CONTRACT PROGRESS
13 |  | READY | 0 |  |  | 100%
of 13 in contract · counts when all 14 codes are released |  | target 13 repeaters · 14 of 14 codes ready | to reach the requested repeaters |  |  | 13 of 13 repeaters kitted
REPEATER COUNTER
Sequence | Assy Code | Description | Qty / Rep | Released | Repeaters | Needed for Request | To Release Now | Status | Repeater
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 13 | 13 | 13 | 0 | READY | Rep 1 · KITTED
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 26 | 13 | 26 | 0 | READY | Rep 2 · KITTED
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 39 | 13 | 39 | 0 | READY | Rep 3 · KITTED
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 13 | 13 | 13 | 0 | READY | Rep 4 · KITTED
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 26 | 13 | 26 | 0 | READY | Rep 5 · KITTED
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 39 | 13 | 39 | 0 | READY | Rep 6 · KITTED
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 312 | 13 | 312 | 0 | READY | Rep 7 · KITTED
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 39 | 13 | 39 | 0 | READY | Rep 8 · KITTED
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 39 | 13 | 39 | 0 | READY | Rep 9 · KITTED
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 39 | 13 | 39 | 0 | READY | Rep 10 · KITTED
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 39 | 13 | 39 | 0 | READY | Rep 11 · KITTED
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 13 | 13 | 13 | 0 | READY | Rep 12 · KITTED
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 13 | 13 | 13 | 0 | READY | Rep 13 · KITTED
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 13 | 13 | 13 | 0 | READY
| TOTAL | Repeaters column total = lowest code (highlighted) — that code limits the count |  | 663 | 13 | 663 | 0
LATEST RELEASES
Date | Assy Code | Description | Qty | Released By | Logged | Note
2026-10-02 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | #182 | Rep 13
2026-10-02 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | #181 | Rep 13
2026-10-02 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | #180 | Rep 13
2026-10-02 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | #179 | Rep 13
2026-10-02 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | #178 | Rep 13
2026-10-02 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | #177 | Rep 13
2026-10-02 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | #176 | Rep 13
2026-10-02 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | #175 | Rep 13

## Contract
CONTRACT — WHAT ONE REPEATER NEEDS
Blue cells are inputs. Change these only when the contract or kitting plan changes.
Contract | R5B
Program | E2A 12FP Cold T5
ERP item | 92ERP12548A++
Config | 12FP
Contract repeaters | 13
Already released before this log started (leave 0 to start fresh)
Sequence | Assy Code | Assy Description | Qty per Repeater | Opening Balance | Contract Qty
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 0 | 13
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 0 | 26
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 0 | 39
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 0 | 13
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 0 | 26
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 0 | 39
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 0 | 312
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 0 | 39
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 0 | 39
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 0 | 39
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 0 | 39
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 0 | 13
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 0 | 13
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 0 | 13

## Release Log
RELEASE LOG
One line per release to production. Type the date, pick the assy code, enter the qty released. The Dashboard counts repeaters from this.
Example: 03-Oct-26 · 92RRA00548AAA · 24 · N.Bakare · for Rep 14
Date | Assy Code | Description | Qty Released | Released By | Note (WO / repeater) | Check
2026-05-06 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 1
2026-05-06 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 1
2026-04-20 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 1
2026-05-14 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 1
2026-05-14 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 1
2026-05-06 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 1
2026-06-03 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 1
2026-05-23 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 1
2026-06-04 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 1
2026-05-23 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 1
2026-05-23 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 1
2026-05-14 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 1
2026-05-18 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 1
2026-05-16 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 1
2026-05-18 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 2
2026-05-19 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 2
2026-05-18 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 2
2026-05-21 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 2
2026-05-21 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 2
2026-05-20 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 2
2026-06-07 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 2
2026-06-03 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 2
2026-06-05 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 2
2026-06-03 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 2
2026-06-03 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 2
2026-05-28 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 2
2026-05-28 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 2
2026-05-28 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 2
2026-05-28 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 3
2026-05-29 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 3
2026-05-28 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 3
2026-06-09 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 3
2026-06-09 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 3
2026-06-09 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 3
2026-07-20 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 3
2026-07-23 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 3
2026-07-23 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 3
2026-07-23 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 3
2026-07-23 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 3
2026-06-17 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 3
2026-06-17 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 3
2026-06-17 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 3
2026-07-28 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 4
2026-07-28 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 4
2026-06-15 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 4
2026-07-31 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 4
2026-07-31 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 4
2026-07-21 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 4
2026-08-04 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 4
2026-08-07 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 4
2026-08-07 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 4
2026-07-29 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 4
2026-08-07 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 4
2026-08-08 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 4
2026-08-08 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 4
2026-08-08 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 4
2026-08-04 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 5
2026-08-09 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 5
2026-07-22 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 5
2026-08-04 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 5
2026-08-10 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 5
2026-08-10 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 5
2026-08-12 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 5
2026-08-12 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 5
2026-08-12 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 5
2026-08-12 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 5
2026-08-12 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 5
2026-08-18 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 5
2026-08-18 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 5
2026-08-18 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 5
2026-08-09 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 6
2026-08-17 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 6
2026-08-09 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 6
2026-08-10 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 6
2026-08-22 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 6
2026-08-22 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 6
2026-08-22 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 6
2026-08-27 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 6
2026-08-27 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 6
2026-08-27 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 6
2026-08-27 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 6
2026-08-29 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 6
2026-08-29 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 6
2026-08-29 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 6
2026-08-17 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 7
2026-09-01 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 7
2026-08-19 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 7
2026-08-22 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 7
2026-09-01 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 7
2026-09-04 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 7
2026-09-07 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 7
2026-09-04 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 7
2026-09-04 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 7
2026-09-04 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 7
2026-09-04 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 7
2026-09-05 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 7
2026-09-05 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 7
2026-09-05 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 7
2026-09-01 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 8
2026-09-11 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 8
2026-08-25 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 8
2026-09-01 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 8
2026-09-13 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 8
2026-09-10 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 8
2026-09-13 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 8
2026-09-16 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 8
2026-09-16 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 8
2026-09-09 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 8
2026-09-16 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 8
2026-09-16 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 8
2026-09-16 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 8
2026-09-16 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 8
2026-09-11 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 9
2026-09-21 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 9
2026-09-08 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 9
2026-09-13 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 9
2026-09-22 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 9
2026-09-22 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 9
2026-09-28 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 9
2026-09-28 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 9
2026-09-28 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 9
2026-09-16 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 9
2026-09-28 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 9
2026-09-29 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 9
2026-09-29 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 9
2026-09-29 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 9
2026-09-21 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 10
2026-10-01 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 10
2026-09-08 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 10
2026-09-22 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 10
2026-10-01 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 10
2026-10-01 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 10
2026-10-01 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 10
2026-10-01 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 10
2026-10-01 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 10
2026-09-28 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 10
2026-10-01 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 10
2026-10-01 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 10
2026-10-01 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 10
2026-10-01 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 10
2026-10-01 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 11
2026-10-01 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 11
2026-09-08 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 11
2026-10-01 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 11
2026-10-01 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 11
2026-10-01 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 11
2026-10-01 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 11
2026-10-01 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 11
2026-10-01 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 11
2026-10-01 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 11
2026-10-01 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 11
2026-10-01 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 11
2026-10-01 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 11
2026-10-01 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 11
2026-10-01 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 12
2026-10-02 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 12
2026-09-11 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 12
2026-10-01 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 12
2026-10-02 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 12
2026-10-02 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 12
2026-10-02 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 12
2026-10-02 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 12
2026-10-02 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 12
2026-10-01 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 12
2026-10-02 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 12
2026-10-02 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 12
2026-10-02 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 12
2026-10-02 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 12
2026-10-02 | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 |  | Rep 13
2026-10-02 | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 |  | Rep 13
2026-09-11 | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 |  | Rep 13
2026-10-02 | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 |  | Rep 13
2026-10-02 | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 |  | Rep 13
2026-10-02 | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 |  | Rep 13
2026-10-02 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 13
2026-10-02 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 13
2026-10-02 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 13
2026-10-02 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 13
2026-10-02 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 13
2026-10-02 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 13
2026-10-02 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 13
2026-10-02 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 13

## How To Use
HOW THE REPEATER COUNTER WORKS
Each time management asks
1. Set the target | Type the number of repeaters requested in the pink cell on the Dashboard (top right).
2. Release | The 'To Release Now' column tells you how many of each assy code to release to reach the target. Release those work orders and send them to production.
3. Log it | On 'Release Log' add one line per release: date, assy code (drop-down), qty released, your name, optional note (WO no. / repeater). Made a mistake? Add a line with a negative qty.
4. Everyone sees it | The Dashboard updates immediately: Repeaters Kitted, the counter, and Latest Releases. Save the file on SharePoint / Teams so everyone sees the same numbers.
How it counts
Repeaters per code | Released qty ÷ qty per repeater, rounded down. E.g. erbium spool: 50 released ÷ 24 = 2 repeaters (2 units toward the 3rd).
Repeaters kitted | The lowest value across all assy codes — a repeater only counts when every code has been released for it. The limiting code is highlighted in the table.
Starting point | If some repeaters were released before you started the log, put those quantities in 'Opening Balance' on the Contract sheet.
Changing the contract | Edit codes, qty per repeater or contract repeaters on the Contract sheet (blue cells). Everything follows.
Projecting | Open the Dashboard and press Ctrl+F1 to hide the ribbon. It fits one landscape screen.