## Dashboard
R5B 24FP KITTING CONTROL · WK 40 | [9 empty] | VIEW REPEATER ▸ | All | Required = release qty
Contract R5B · WKE-R24P-T1-C · 92ERP24543A++ · 24FP · Repeaters 1-3 · 3 to release | [10 empty] | Pick All, 1, 2 or 3
ASSEMBLIES |  | REQUIRED QTY | WO COVERAGE |  |  | WORK ORDERS |  | SHORT / OVER |  | DATA FLAGS
16 |  | 264 | 0% |  |  | 0 |  | 0 |  | 1
6 sequences · 0 fully covered |  | units · release across 3 repeaters | 0 of 264 units on WOs |  |  | 0 closed · 16 codes with no WO |  | 0 short · 0 over |  | 1 plan qty checks · 0 WO entry flags
COVERAGE BY SEQUENCE | [6 empty] | WORK-ORDER PIPELINE
Sequence | Codes | Coverage | Required | WO Qty | % |  | Status | WOs | Qty | Share of WOs
LASER ASSY | 3 | 0 | 9 | 0 | 0% |  | Planned | 0 | 0 | 0%
PSB ASSY | 1 | 0 | 18 | 0 | 0% |  | Released | 0 | 0 | 0%
OPF ASSY | 3 | 0 | 9 | 0 | 0% |  | Kitted | 0 | 0 | 0%
POB ASSY | 1 | 0 | 18 | 0 | 0% |  | Closed | 0 | 0 | 0%
ERBIUM ASSY | 5 | 0 | 201 | 0 | 0% |  | Total | 0 | 0
BOAT ASSY | 3 | 0 | 9 | 0 | 0% |  | ⚠ 1 code(s): release qty ≠ default × repeaters — see Plan Check column
ASSEMBLY LEDGER |  | Coverage = WO qty ÷ required qty for the selected view. Repeater views count each 'All' WO as one third per repeater.
Sequence | Assy Code | Description | Release | Default / Rep | Required | WO Qty | Coverage | Status | WOs | Closed Qty | Work Order Nos. | Plan Check
LASER ASSY | 92YLS00543AAA | R5B LASER ASSEMBLY 4P-4P BOAT 1 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
LASER ASSY | 92YLS00543ABA | R5B LASER ASSEMBLY 4P-4P BOAT 2 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
LASER ASSY | 92YLS00543ACA | R5B LASER ASSEMBLY 4P-4P BOAT 3 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 18 | 6 | 18 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
OPF ASSY | 92YFD44543AAA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 1 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
OPF ASSY | 92YFD44543ABA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 2 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
OPF ASSY | 92YFD44543ACA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 3 - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
POB ASSY | 92YWS04543AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - WKE | 18 | 6 | 18 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA01543AAA | R5B ERBIUM ASSEMBLY 1 - WKE | 18 | 6 | 18 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA02543AAA | R5B ERBIUM ASSEMBLY 2 - WKE | 3 | 6 | 3 | 0 | 0% | NO WO | 0 | 0 |  | CHECK: release ≠ default × reps (18) | 0
ERBIUM ASSY | 92YRA03543AAA | R5B ERBIUM ASSEMBLY 3 - WKE | 18 | 6 | 18 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92YRA04543AAA | R5B ERBIUM ASSEMBLY 4 - WKE | 18 | 6 | 18 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
ERBIUM ASSY | 92RRA00543AAA | R5B ERBIUM SPOOL ASSEMBLY - WKE | 144 | 48 | 144 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP44543AAA | R5B BOAT 1 ASSY 2X(4P-4FP) L - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP44543ABA | R5B BOAT 2 ASSY 2X(4P-4FP) L - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0
BOAT ASSY | 92UAP44543ACA | R5B BOAT 3 ASSY 2X(4P-4FP) L - WKE | 3 | 1 | 3 | 0 | 0% | NO WO | 0 | 0 |  | OK | 0

## Kitting Plan
KITTING PLAN — MASTER DATA
Source: kitting plan table supplied by the user (R5B · WKE-R24P-T1-C · 92ERP24543A++ · 24FP · WK 40). Blue cells are inputs; edit them when the plan changes.
Contract | Sequence | Assy Code | Assy Description | Release | Repeater No. | No. of Rep to Rel | Default Qty | Check
R5B | LASER ASSY | 92YLS00543AAA | R5B LASER ASSEMBLY 4P-4P BOAT 1 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | LASER ASSY | 92YLS00543ABA | R5B LASER ASSEMBLY 4P-4P BOAT 2 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | LASER ASSY | 92YLS00543ACA | R5B LASER ASSEMBLY 4P-4P BOAT 3 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 18 | 1-3 | 3 | 6 | OK
R5B | OPF ASSY | 92YFD44543AAA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 1 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | OPF ASSY | 92YFD44543ABA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 2 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | OPF ASSY | 92YFD44543ACA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 3 - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | POB ASSY | 92YWS04543AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - WKE | 18 | 1-3 | 3 | 6 | OK
R5B | ERBIUM ASSY | 92YRA01543AAA | R5B ERBIUM ASSEMBLY 1 - WKE | 18 | 1-3 | 3 | 6 | OK
R5B | ERBIUM ASSY | 92YRA02543AAA | R5B ERBIUM ASSEMBLY 2 - WKE | 3 | 1-3 | 3 | 6 | CHECK: release ≠ default × reps (18)
R5B | ERBIUM ASSY | 92YRA03543AAA | R5B ERBIUM ASSEMBLY 3 - WKE | 18 | 1-3 | 3 | 6 | OK
R5B | ERBIUM ASSY | 92YRA04543AAA | R5B ERBIUM ASSEMBLY 4 - WKE | 18 | 1-3 | 3 | 6 | OK
R5B | ERBIUM ASSY | 92RRA00543AAA | R5B ERBIUM SPOOL ASSEMBLY - WKE | 144 | 1-3 | 3 | 48 | OK
R5B | BOAT ASSY | 92UAP44543AAA | R5B BOAT 1 ASSY 2X(4P-4FP) L - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | BOAT ASSY | 92UAP44543ABA | R5B BOAT 2 ASSY 2X(4P-4FP) L - WKE | 3 | 1-3 | 3 | 1 | OK
R5B | BOAT ASSY | 92UAP44543ACA | R5B BOAT 3 ASSY 2X(4P-4FP) L - WKE | 3 | 1-3 | 3 | 1 | OK
Contract details shown on the Dashboard
Contract | R5B
Program | WKE-R24P-T1-C
ERP item | 92ERP24543A++
Config | 24FP
Kitting week | WK 40
Repeaters | 1-3 · 3 to release

## Work Orders
WORK ORDERS
Type the WO number and pick the assy code. Quantity fills in automatically from the kitting plan (release qty, or default qty when a single repeater is chosen).
Blue columns = you type. Grey columns = automatic. Use 'Qty Override' only when the WO quantity differs from the plan.
|  |  |  | Blank = All |  | Leave blank to use Listed Qty |  | Blank = Planned
WO No. | Assy Code | Description | Sequence | Repeater | Listed Qty | Qty Override | WO Qty | Status | Release Date | Remarks | Flag

## Lists (hidden)
92YLS00543AAA
92YLS00543ABA
92YLS00543ACA
91YAF03404AAA
92YFD44543AAA
92YFD44543ABA
92YFD44543ACA
92YWS04543AAA
92YRA01543AAA
92YRA02543AAA
92YRA03543AAA
92YRA04543AAA
92RRA00543AAA
92UAP44543AAA
92UAP44543ABA
92UAP44543ACA

## How To Use
HOW TO USE THIS WORKBOOK
For the team
1. Add a work order | Go to 'Work Orders'. Type the WO number in column A and pick the assy code in column B. Description, sequence and quantity fill in by themselves.
2. Quantity | WO Qty = the listed qty from the kitting plan (release qty, e.g. 144 for 92RRA00543AAA). If you pick repeater 1, 2 or 3 it uses the default qty instead (e.g. 48). Type in 'Qty Override' only if the WO is for a different quantity.
3. Update status | Change 'Status' as the WO moves: Planned → Released → Kitted → Closed. Blank counts as Planned.
Example entry | WO No. = WO-4012871 · Assy Code = 92YLS00543AAA · Repeater = All · Qty Override = (blank) · Status = Released
Flags | Column L on 'Work Orders' warns about duplicate WO numbers, missing codes or codes not in the plan.
For management
Dashboard | Shows the whole plan on one screen: totals at the top, coverage by sequence, the WO pipeline, and every assembly with its WOs.
Read the Status column | NO WO = nothing raised yet · SHORT n = WOs cover less than required (n units missing) · COVERED = WO qty matches · OVER = more WO qty than required.
Trace a WO | The 'Work Order Nos.' column lists every WO on each assy code. To go the other way, filter column A on 'Work Orders'.
Switch repeater view | Pick All, 1, 2 or 3 in the pink cell at the top right of the Dashboard. 'All' checks against release qty; 1/2/3 checks against the default qty for that repeater.
Projecting on a screen | Open the Dashboard tab, press Ctrl+F1 to hide the ribbon, then View → Zoom → 'Zoom to Selection' on B2:N36 (or set zoom to fit your screen). Excel recalculates as soon as anyone adds a WO.
Live sharing | Save the file on SharePoint / OneDrive / Teams so several people can edit while the dashboard is on screen.
Changing the plan | Edit the blue cells on 'Kitting Plan' (codes, release qty, default qty). The Dashboard and WO lookups follow automatically.
Known plan check | 92YRA02543AAA has release 3 but default 6 × 3 repeaters = 18. It's flagged in the Plan Check column until confirmed.