## Dashboard
R5B AMP KITTING CONTROL | [10 empty] | DATE | 2026-10-05
CONTRACT ▸ |  | E2A-R12P-T5-C |  |  | TOTAL REPS | 109 | AMPS / REP | 12 |  |  | AS OF ▸ | 2026-10-05 | 2
E2A · top code 92ERP12548A++ · 12FP · 14 sub-assemblies per repeater | [11 empty] | Week 41
REPEATERS KITTED |  | AMPS KITTED | PLAN TO DATE |  |  | VS PLAN |  |  | NEXT 4 WEEKS | LAST RELEASE
13 / 109 |  | 156 | 31 |  |  | -18 |  |  | 2 | 2026-10-02
12% of contract · 96 to go |  | of 1,308 amps (12 per repeater) | kits due by Week 41 (housing W43, 2-wk lead) |  |  | BEHIND -18 |  |  | repeaters to kit next 4 weeks | 182 release lines logged
CONTRACT PROGRESS |  | 11.93%
SUB-ASSEMBLIES |  |  |  | RELEASE TARGET ▸ |  |  | 33 | reps · type to override | PLAN VS KITTED (repeaters, cumulative)
Sequence | Assy Code | Description | Qty / Rep | Released | Repeaters | Toward Next | Needed for Target | To Release
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 13 | 13 | 0 / 1 | 33 | 20
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 26 | 13 | 0 / 2 | 66 | 40
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 39 | 13 | 0 / 3 | 99 | 60
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 13 | 13 | 0 / 1 | 33 | 20
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 26 | 13 | 0 / 2 | 66 | 40
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 39 | 13 | 0 / 3 | 99 | 60
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 312 | 13 | 0 / 24 | 792 | 480
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 39 | 13 | 0 / 3 | 99 | 60
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 39 | 13 | 0 / 3 | 99 | 60
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 39 | 13 | 0 / 3 | 99 | 60
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 39 | 13 | 0 / 3 | 99 | 60
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 13 | 13 | 0 / 1 | 33 | 20
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 13 | 13 | 0 / 1 | 33 | 20
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 13 | 13 | 0 / 1 | 33 | 20
| TOTAL | Repeaters = lowest sub-assembly (highlighted red) — it limits the count |  | 663 | 13 |  | 1683 | 1020
LATEST RELEASES (this contract)
Date | Assy Code | Description | Qty | Released By | Note
2026-10-02 | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 |  | Rep 13 (from COOIS)
2026-10-02 | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 |  | Rep 13 (from COOIS)
2026-10-02 | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 |  | Rep 13 (from COOIS)
2026-10-02 | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 |  | Rep 13 (from COOIS)
2026-10-02 | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 |  | Rep 13 (from COOIS)
2026-10-02 | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 |  | Rep 13 (from COOIS)
2026-10-02 | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 |  | Rep 13 (from COOIS)
2026-10-02 | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 |  | Rep 13 (from COOIS)
Note on Q2: Leave =TODAY() or type a date to view the position as of that week.

## Portfolio
R5B AMP KITTING — ALL CONTRACTS
As of 05-Oct-26 · week 41 · 12 contracts
Contract | Project | Top Code | FP | Total Reps | Kitted | Progress | Amps Kitted | Plan to Date | Vs Plan | Status
WKE-R24P-T1-C | Wamkelekile | 92ERP24543A++ | 24 | 255 | 0 | 0% | 0 | 0 | 0 | ON PLAN
WBA-R24P-T1-C | Waban | 92ERP24545A++ | 24 | 200 | – | – | – | 0 | – | NO KIT LIST
E2A-R4P-T1-C | E2A | 92ERP04548A++ | 4 | 39 | – | – | – | 0 | – | NO KIT LIST
E2A-R4P-T2-M | E2A | 92ERP04548B++ | 4 | 11 | – | – | – | 0 | – | NO KIT LIST
E2A-R6P-T3-M | E2A | 92ERP06548A++ | 6 | 3 | – | – | – | 0 | – | NO KIT LIST
E2A-R8P-T4-C | E2A | 92ERP08548A++ | 8 | 10 | – | – | – | 0 | – | NO KIT LIST
E2A-R12P-T5-C | E2A | 92ERP12548A++ | 12 | 109 | 13 | 11.93% | 156 | 31 | -18 | BEHIND -18
E2A-R12P-T6-C | E2A | 92ERP12548B++ | 12 | 5 | – | – | – | 0 | – | NO KIT LIST
E2A-R16P-T7-C | E2A | 92ERP16548A++ | 16 | 9 | – | – | – | 0 | – | NO KIT LIST
DARAJA-R8P (TBC) | Daraja Ext to SA | Not yet released | 8 | 10 | – | – | – | 0 | – | NO KIT LIST
DARAJA-R24P (TBC) | Daraja Ext to SA | Not yet released | 24 | 46 | – | – | – | 0 | – | NO KIT LIST
REUNION-SOUTH-R16P (TBC) | Reunion-South Africa (wet plant only) | Not yet released | 16 | 31 | – | – | – | 0 | – | NO KIT LIST

## Gantt
R5B AMP KITTING — RELEASE GANTT
Repeater numbers per ISO week · housing (final build) = plan week W · AMPS build = W−1 · kit release = W−lead (Contracts, default 2) · as of 05-Oct-26 (W41)
START WEEK (Mon) ▸ | 2026-08-24 |  | Kit planned |  | Kitted |  | Kit overdue |  | AMPS build |  | Housing / final |  | This week
|  |  | 2026 | [18 empty] | 2027
Contract | Stage | Reps | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33
 | time axis 2026-08-24 to 2027-08-16
WKE-R24P-T1-C | Kit release | 32 wks | [7 empty] | R1 | R2 | R3 | R4 | R5-6 | R7 | [7 empty] | R8 | R9-12 | R13-15 | R16-19 | R20-23 | R24-27 | R28-32 | R33-36 | R37-40 | R41-45 | R46-49 | R50-52 | R53-56 | R57-60 | R61-62 | R63 | [6 empty] | R64-68 | R69-74 | R75-81 | R82-88 | R89-95 | R96-102 | R103-109 | R110-116 | R117-124 | R125-131
92ERP24543A++ | AMPS build | 31 wks | 2026-10-19: R1; 2026-10-26: R2; 2026-11-02: R3; 2026-11-09: R4; 2026-11-16: R5-6; 2026-11-23: R7; 2027-01-18: R8; 2027-01-25: R9-12; 2027-02-01: R13-15; 2027-02-08: R16-19; 2027-02-15: R20-23; 2027-02-22: R24-27; 2027-03-01: R28-32; 2027-03-08: R33-36; 2027-03-15: R37-40; 2027-03-22: R41-45; 2027-03-29: R46-49; 2027-04-05: R50-52; 2027-04-12: R53-56; 2027-04-19: R57-60; 2027-04-26: R61-62; 2027-05-03: R63; 2027-06-21: R64-68; 2027-06-28: R69-74; 2027-07-05: R75-81; 2027-07-12: R82-88; 2027-07-19: R89-95; 2027-07-26: R96-102; 2027-08-02: R103-109; 2027-08-09: R110-116; 2027-08-16: R117-124
kitted: 0 / 255 | Final build | 30 wks | 2026-10-26: R1; 2026-11-02: R2; 2026-11-09: R3; 2026-11-16: R4; 2026-11-23: R5-6; 2026-11-30: R7; 2027-01-25: R8; 2027-02-01: R9-12; 2027-02-08: R13-15; 2027-02-15: R16-19; 2027-02-22: R20-23; 2027-03-01: R24-27; 2027-03-08: R28-32; 2027-03-15: R33-36; 2027-03-22: R37-40; 2027-03-29: R41-45; 2027-04-05: R46-49; 2027-04-12: R50-52; 2027-04-19: R53-56; 2027-04-26: R57-60; 2027-05-03: R61-62; 2027-05-10: R63; 2027-06-28: R64-68; 2027-07-05: R69-74; 2027-07-12: R75-81; 2027-07-19: R82-88; 2027-07-26: R89-95; 2027-08-02: R96-102; 2027-08-09: R103-109; 2027-08-16: R110-116
WBA-R24P-T1-C | Kit release | 0 wks
92ERP24545A++ | AMPS build | 0 wks
no kit list | Final build | 0 wks
E2A-R4P-T1-C | Kit release | 6 wks | 2026-10-26: R1-5; 2026-11-02: R6-11; 2026-11-09: R12; 2026-11-16: R13-20; 2026-11-23: R21-28; 2027-01-11: R29-39
92ERP04548A++ | AMPS build | 6 wks | 2026-11-02: R1-5; 2026-11-09: R6-11; 2026-11-16: R12; 2026-11-23: R13-20; 2026-11-30: R21-28; 2027-01-18: R29-39
no kit list | Final build | 6 wks | 2026-11-09: R1-5; 2026-11-16: R6-11; 2026-11-23: R12; 2026-11-30: R13-20; 2026-12-07: R21-28; 2027-01-25: R29-39
E2A-R4P-T2-M | Kit release | 6 wks | 2027-04-05: R1; 2027-04-19: R2-3; 2027-04-26: R4-8; 2027-05-24: R9; 2027-05-31: R10; 2027-06-07: R11
92ERP04548B++ | AMPS build | 6 wks | 2027-04-12: R1; 2027-04-26: R2-3; 2027-05-03: R4-8; 2027-05-31: R9; 2027-06-07: R10; 2027-06-14: R11
no kit list | Final build | 6 wks | 2027-04-19: R1; 2027-05-03: R2-3; 2027-05-10: R4-8; 2027-06-07: R9; 2027-06-14: R10; 2027-06-21: R11
E2A-R6P-T3-M | Kit release | 1 wks | 2027-03-08: R1-3
92ERP06548A++ | AMPS build | 1 wks | 2027-03-15: R1-3
no kit list | Final build | 1 wks | 2027-03-22: R1-3
E2A-R8P-T4-C | Kit release | 2 wks | 2026-11-30: R1-8; 2026-12-21: R9-10
92ERP08548A++ | AMPS build | 2 wks | 2026-12-07: R1-8; 2026-12-28: R9-10
no kit list | Final build | 2 wks | 2026-12-14: R1-8; 2027-01-04: R9-10
E2A-R12P-T5-C | Kit release | 23 wks | 2026-08-31: R20; 2026-09-07: R21-22; 2026-09-14: R23-24; 2026-09-21: R25-26; 2026-09-28: R27-28; 2026-10-05: R29-31; 2026-10-12: R32; 2026-10-19: R33; 2026-11-23: R34-35; 2026-12-21: R36-44; 2026-12-28: R45-46; 2027-01-04: R47-52; 2027-04-05: R53; 2027-04-12: R54; 2027-04-19: R55; 2027-04-26: R56-60; 2027-05-03: R61-67; 2027-05-10: R68-79; 2027-05-17: R80-90; 2027-05-24: R91-102; 2027-05-31: R103-113; 2027-06-07: R114-124; 2027-06-14: R125-126
92ERP12548A++ | AMPS build | 24 wks | 2026-08-24: R18-19; 2026-09-07: R20; 2026-09-14: R21-22; 2026-09-21: R23-24; 2026-09-28: R25-26; 2026-10-05: R27-28; 2026-10-12: R29-31; 2026-10-19: R32; 2026-10-26: R33; 2026-11-30: R34-35; 2026-12-28: R36-44; 2027-01-04: R45-46; 2027-01-11: R47-52; 2027-04-12: R53; 2027-04-19: R54; 2027-04-26: R55; 2027-05-03: R56-60; 2027-05-10: R61-67; 2027-05-17: R68-79; 2027-05-24: R80-90; 2027-05-31: R91-102; 2027-06-07: R103-113; 2027-06-14: R114-124; 2027-06-21: R125-126
kitted: 13 / 109 | Final build | 25 wks | 2026-08-24: R15-17; 2026-08-31: R18-19; 2026-09-14: R20; 2026-09-21: R21-22; 2026-09-28: R23-24; 2026-10-05: R25-26; 2026-10-12: R27-28; 2026-10-19: R29-31; 2026-10-26: R32; 2026-11-02: R33; 2026-12-07: R34-35; 2027-01-04: R36-44; 2027-01-11: R45-46; 2027-01-18: R47-52; 2027-04-19: R53; 2027-04-26: R54; 2027-05-03: R55; 2027-05-10: R56-60; 2027-05-17: R61-67; 2027-05-24: R68-79; 2027-05-31: R80-90; 2027-06-07: R91-102; 2027-06-14: R103-113; 2027-06-21: R114-124; 2027-06-28: R125-126
E2A-R12P-T6-C | Kit release | 3 wks | 2027-04-05: R1-2; 2027-04-12: R3; 2027-06-14: R4-5
92ERP12548B++ | AMPS build | 3 wks | 2027-04-12: R1-2; 2027-04-19: R3; 2027-06-21: R4-5
no kit list | Final build | 3 wks | 2027-04-19: R1-2; 2027-04-26: R3; 2027-06-28: R4-5
E2A-R16P-T7-C | Kit release | 4 wks | 2027-03-29: R1-2; 2027-04-19: R3-6; 2027-04-26: R7; 2027-05-03: R8-9
92ERP16548A++ | AMPS build | 4 wks | 2027-04-05: R1-2; 2027-04-26: R3-6; 2027-05-03: R7; 2027-05-10: R8-9
no kit list | Final build | 4 wks | 2027-04-12: R1-2; 2027-05-03: R3-6; 2027-05-10: R7; 2027-05-17: R8-9
DARAJA-R8P (TBC) | Kit release | 0 wks
Not yet released | AMPS build | 0 wks
no kit list | Final build | 0 wks
DARAJA-R24P (TBC) | Kit release | 0 wks
Not yet released | AMPS build | 0 wks
no kit list | Final build | 0 wks
REUNION-SOUTH-R16P (TBC) | Kit release | 0 wks
Not yet released | AMPS build | 0 wks
no kit list | Final build | 0 wks
Note on C4: Defaults to 6 weeks before today. Type any Monday (e.g. 01/06/2026) to scroll the Gantt.

## Contracts
CONTRACTS — R5B AMP KITTING
One row per top-level code (++). Blue = inputs. Total repeaters can change when batches change (e.g. 109 → 117).
Contract (Friendly name) | Project | Top Code (++) | FP | Amps / Repeater | Total Repeaters | Notes | Kit Lines | Repeaters Kitted | Amps Kitted | Plan to Date | Vs Plan | Total in Weekly Plan | % Kitted | Status | Last Release | Kit Lead (wks)
WKE-R24P-T1-C | Wamkelekile | 92ERP24543A++ | 24 | 24 | 255 |  | 16 | 0 | 0 | 0 | 0 | 255 | 0% | ON PLAN | – | 2
WBA-R24P-T1-C | Waban | 92ERP24545A++ | 24 | 24 | 200 |  | 0 |  |  | 0 |  | 200 |  | NO KIT LIST | – | 2
E2A-R4P-T1-C | E2A | 92ERP04548A++ | 4 | 4 | 39 |  | 0 |  |  | 0 |  | 39 |  | NO KIT LIST | – | 2
E2A-R4P-T2-M | E2A | 92ERP04548B++ | 4 | 4 | 11 |  | 0 |  |  | 0 |  | 11 |  | NO KIT LIST | – | 2
E2A-R6P-T3-M | E2A | 92ERP06548A++ | 6 | 6 | 3 |  | 0 |  |  | 0 |  | 3 |  | NO KIT LIST | – | 2
E2A-R8P-T4-C | E2A | 92ERP08548A++ | 8 | 8 | 10 |  | 0 |  |  | 0 |  | 10 |  | NO KIT LIST | – | 2
E2A-R12P-T5-C | E2A | 92ERP12548A++ | 12 | 12 | 109 |  | 14 | 13 | 156 | 31 | -18 | 126 | 11.93% | BEHIND -18 | 2026-10-02 | 2
E2A-R12P-T6-C | E2A | 92ERP12548B++ | 12 | 12 | 5 |  | 0 |  |  | 0 |  | 5 |  | NO KIT LIST | – | 2
E2A-R16P-T7-C | E2A | 92ERP16548A++ | 16 | 16 | 9 |  | 0 |  |  | 0 |  | 9 |  | NO KIT LIST | – | 2
DARAJA-R8P (TBC) | Daraja Ext to SA | Not yet released | 8 | 8 | 10 | Top code not yet released | 0 |  |  | 0 |  | 10 |  | NO KIT LIST | – | 2
DARAJA-R24P (TBC) | Daraja Ext to SA | Not yet released | 24 | 24 | 46 | Top code not yet released | 0 |  |  | 0 |  | 46 |  | NO KIT LIST | – | 2
REUNION-SOUTH-R16P (TBC) | Reunion-South Africa (wet plant only) | Not yet released | 16 | 16 | 31 | Top code not yet released | 0 |  |  | 0 |  | 31 |  | NO KIT LIST | – | 2
Formulas:
Last Release = IF([Contract (Friendly name)]="","",IF(COUNTIF('Release Log'!$B6:B4005,[Contract (Friendly name)])=0,"–",MAXIFS('Release Log'!$A6:A4005,'Release Log'!$B6:B4005,[Contract (Friendly name)])))

## Kit Lists
KIT LISTS — SUB-ASSEMBLIES PER REPEATER (ZMRP BREAKDOWN)
One row per sub-assembly per contract: how many go into ONE repeater. Enter once per contract. Blue = inputs; grey columns calculate.
Contract | Sequence | Assy Code | Assy Description | Qty per Repeater | Slot | Key | Released | Repeaters Kitted | Lookup
E2A-R12P-T5-C | LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 1 | E2A-R12P-T5-C¦1 | 13 | 13 | E2A-R12P-T5-C¦92YLS00548BAA
E2A-R12P-T5-C | LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 2 | E2A-R12P-T5-C¦2 | 26 | 13 | E2A-R12P-T5-C¦92YLS00548BBA
E2A-R12P-T5-C | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 3 | E2A-R12P-T5-C¦3 | 39 | 13 | E2A-R12P-T5-C¦91YAF03404AAA
E2A-R12P-T5-C | OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 4 | E2A-R12P-T5-C¦4 | 13 | 13 | E2A-R12P-T5-C¦92YFD04548BAA
E2A-R12P-T5-C | OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 5 | E2A-R12P-T5-C¦5 | 26 | 13 | E2A-R12P-T5-C¦92YFD04548BBA
E2A-R12P-T5-C | POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 6 | E2A-R12P-T5-C¦6 | 39 | 13 | E2A-R12P-T5-C¦92YWS04548AAA
E2A-R12P-T5-C | ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 7 | E2A-R12P-T5-C¦7 | 312 | 13 | E2A-R12P-T5-C¦92RRA00548AAA
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 8 | E2A-R12P-T5-C¦8 | 39 | 13 | E2A-R12P-T5-C¦92YRA01548AAA
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 9 | E2A-R12P-T5-C¦9 | 39 | 13 | E2A-R12P-T5-C¦92YRA02548AAA
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 10 | E2A-R12P-T5-C¦10 | 39 | 13 | E2A-R12P-T5-C¦92YRA03548AAA
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 11 | E2A-R12P-T5-C¦11 | 39 | 13 | E2A-R12P-T5-C¦92YRA04548AAA
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 12 | E2A-R12P-T5-C¦12 | 13 | 13 | E2A-R12P-T5-C¦92UAP04548BAA
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 13 | E2A-R12P-T5-C¦13 | 13 | 13 | E2A-R12P-T5-C¦92UAP04548BBA
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 14 | E2A-R12P-T5-C¦14 | 13 | 13 | E2A-R12P-T5-C¦92UAP04548BCA
WKE-R24P-T1-C | LASER ASSY | 92YLS00543AAA | R5B LASER ASSEMBLY 4P-4P BOAT 1 - WKE | 1 | 1 | WKE-R24P-T1-C¦1 | 0 | 0 | WKE-R24P-T1-C¦92YLS00543AAA
WKE-R24P-T1-C | LASER ASSY | 92YLS00543ABA | R5B LASER ASSEMBLY 4P-4P BOAT 2 - WKE | 1 | 2 | WKE-R24P-T1-C¦2 | 0 | 0 | WKE-R24P-T1-C¦92YLS00543ABA
WKE-R24P-T1-C | LASER ASSY | 92YLS00543ACA | R5B LASER ASSEMBLY 4P-4P BOAT 3 - WKE | 1 | 3 | WKE-R24P-T1-C¦3 | 0 | 0 | WKE-R24P-T1-C¦92YLS00543ACA
WKE-R24P-T1-C | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 6 | 4 | WKE-R24P-T1-C¦4 | 0 | 0 | WKE-R24P-T1-C¦91YAF03404AAA
WKE-R24P-T1-C | OPF ASSY | 92YFD44543AAA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 1 - WKE | 1 | 5 | WKE-R24P-T1-C¦5 | 0 | 0 | WKE-R24P-T1-C¦92YFD44543AAA
WKE-R24P-T1-C | OPF ASSY | 92YFD44543ABA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 2 - WKE | 1 | 6 | WKE-R24P-T1-C¦6 | 0 | 0 | WKE-R24P-T1-C¦92YFD44543ABA
WKE-R24P-T1-C | OPF ASSY | 92YFD44543ACA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 3 - WKE | 1 | 7 | WKE-R24P-T1-C¦7 | 0 | 0 | WKE-R24P-T1-C¦92YFD44543ACA
WKE-R24P-T1-C | POB ASSY | 92YWS04543AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - WKE | 6 | 8 | WKE-R24P-T1-C¦8 | 0 | 0 | WKE-R24P-T1-C¦92YWS04543AAA
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA01543AAA | R5B ERBIUM ASSEMBLY 1 - WKE | 6 | 9 | WKE-R24P-T1-C¦9 | 0 | 0 | WKE-R24P-T1-C¦92YRA01543AAA
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA02543AAA | R5B ERBIUM ASSEMBLY 2 - WKE | 6 | 10 | WKE-R24P-T1-C¦10 | 0 | 0 | WKE-R24P-T1-C¦92YRA02543AAA
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA03543AAA | R5B ERBIUM ASSEMBLY 3 - WKE | 6 | 11 | WKE-R24P-T1-C¦11 | 0 | 0 | WKE-R24P-T1-C¦92YRA03543AAA
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA04543AAA | R5B ERBIUM ASSEMBLY 4 - WKE | 6 | 12 | WKE-R24P-T1-C¦12 | 0 | 0 | WKE-R24P-T1-C¦92YRA04543AAA
WKE-R24P-T1-C | ERBIUM ASSY | 92RRA00543AAA | R5B ERBIUM SPOOL ASSEMBLY - WKE | 48 | 13 | WKE-R24P-T1-C¦13 | 0 | 0 | WKE-R24P-T1-C¦92RRA00543AAA
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543AAA | R5B BOAT 1 ASSY 2X(4P-4FP) L - WKE | 1 | 14 | WKE-R24P-T1-C¦14 | 0 | 0 | WKE-R24P-T1-C¦92UAP44543AAA
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543ABA | R5B BOAT 2 ASSY 2X(4P-4FP) L - WKE | 1 | 15 | WKE-R24P-T1-C¦15 | 0 | 0 | WKE-R24P-T1-C¦92UAP44543ABA
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543ACA | R5B BOAT 3 ASSY 2X(4P-4FP) L - WKE | 1 | 16 | WKE-R24P-T1-C¦16 | 0 | 0 | WKE-R24P-T1-C¦92UAP44543ACA

## Weekly Plan
WEEKLY RELEASE PLAN — REPEATERS TO KIT PER WEEK
Release weeks from the plan / CO41. One row per contract per week. Only weeks with a quantity are needed.
Contract | ISO Year | ISO Week | Repeaters to Release | Week Starts (Mon) | Note
WKE-R24P-T1-C | 2026 | 44 | 1 | 2026-10-26 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026 | 45 | 1 | 2026-11-02 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026 | 46 | 1 | 2026-11-09 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026 | 47 | 1 | 2026-11-16 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026 | 48 | 2 | 2026-11-23 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026 | 49 | 1 | 2026-11-30 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 4 | 1 | 2027-01-25 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 5 | 4 | 2027-02-01 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 6 | 3 | 2027-02-08 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 7 | 4 | 2027-02-15 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 8 | 4 | 2027-02-22 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 9 | 4 | 2027-03-01 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 10 | 5 | 2027-03-08 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 11 | 4 | 2027-03-15 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 12 | 4 | 2027-03-22 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 13 | 5 | 2027-03-29 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 14 | 4 | 2027-04-05 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 15 | 3 | 2027-04-12 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 16 | 4 | 2027-04-19 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 17 | 4 | 2027-04-26 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 18 | 2 | 2027-05-03 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 19 | 1 | 2027-05-10 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 26 | 5 | 2027-06-28 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 27 | 6 | 2027-07-05 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 28 | 7 | 2027-07-12 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 29 | 7 | 2027-07-19 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 30 | 7 | 2027-07-26 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 31 | 7 | 2027-08-02 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 32 | 7 | 2027-08-09 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 33 | 7 | 2027-08-16 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 34 | 8 | 2027-08-23 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 35 | 7 | 2027-08-30 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 36 | 7 | 2027-09-06 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 37 | 6 | 2027-09-13 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 38 | 8 | 2027-09-20 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 39 | 7 | 2027-09-27 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 40 | 7 | 2027-10-04 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 41 | 7 | 2027-10-11 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 42 | 5 | 2027-10-18 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 43 | 7 | 2027-10-25 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 44 | 8 | 2027-11-01 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 45 | 7 | 2027-11-08 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 46 | 7 | 2027-11-15 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 47 | 7 | 2027-11-22 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 48 | 7 | 2027-11-29 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 49 | 7 | 2027-12-06 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 50 | 8 | 2027-12-13 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027 | 51 | 7 | 2027-12-20 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2028 | 2 | 12 | 2028-01-10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2027 | 42 | 2 | 2027-10-18 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 2 | 1 | 2028-01-10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 4 | 8 | 2028-01-24 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 5 | 7 | 2028-01-31 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 6 | 7 | 2028-02-07 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 7 | 8 | 2028-02-14 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 8 | 8 | 2028-02-21 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 9 | 8 | 2028-02-28 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 10 | 8 | 2028-03-06 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 11 | 9 | 2028-03-13 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 12 | 9 | 2028-03-20 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 13 | 9 | 2028-03-27 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 14 | 9 | 2028-04-03 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 15 | 10 | 2028-04-10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 16 | 3 | 2028-04-17 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 17 | 2 | 2028-04-24 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 18 | 10 | 2028-05-01 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 19 | 9 | 2028-05-08 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 20 | 10 | 2028-05-15 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 21 | 9 | 2028-05-22 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 22 | 10 | 2028-05-29 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 23 | 9 | 2028-06-05 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 24 | 10 | 2028-06-12 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 25 | 9 | 2028-06-19 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 26 | 10 | 2028-06-26 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 27 | 3 | 2028-07-03 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028 | 28 | 3 | 2028-07-10 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026 | 46 | 5 | 2026-11-09 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026 | 47 | 6 | 2026-11-16 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026 | 48 | 1 | 2026-11-23 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026 | 49 | 8 | 2026-11-30 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026 | 50 | 8 | 2026-12-07 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2027 | 4 | 11 | 2027-01-25 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 16 | 1 | 2027-04-19 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 18 | 2 | 2027-05-03 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 19 | 5 | 2027-05-10 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 23 | 1 | 2027-06-07 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 24 | 1 | 2027-06-14 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027 | 25 | 1 | 2027-06-21 | PLAN export 02-Sep-26
E2A-R6P-T3-M | 2027 | 12 | 3 | 2027-03-22 | PLAN export 02-Sep-26
E2A-R8P-T4-C | 2026 | 51 | 8 | 2026-12-14 | PLAN export 02-Sep-26
E2A-R8P-T4-C | 2027 | 1 | 2 | 2027-01-04 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 24 | 1 | 2026-06-08 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 27 | 1 | 2026-06-29 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 28 | 1 | 2026-07-06 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 29 | 1 | 2026-07-13 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 30 | 2 | 2026-07-20 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 31 | 2 | 2026-07-27 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 32 | 2 | 2026-08-03 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 33 | 2 | 2026-08-10 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 34 | 2 | 2026-08-17 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 35 | 3 | 2026-08-24 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026 | 36 | 2 | 2026-08-31 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 38 | 1 | 2026-09-14 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 39 | 2 | 2026-09-21 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 40 | 2 | 2026-09-28 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 41 | 2 | 2026-10-05 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 42 | 2 | 2026-10-12 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 43 | 3 | 2026-10-19 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 44 | 1 | 2026-10-26 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 45 | 1 | 2026-11-02 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026 | 50 | 2 | 2026-12-07 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 1 | 9 | 2027-01-04 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 2 | 2 | 2027-01-11 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 3 | 6 | 2027-01-18 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 16 | 1 | 2027-04-19 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 17 | 1 | 2027-04-26 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 18 | 1 | 2027-05-03 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 19 | 5 | 2027-05-10 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 20 | 7 | 2027-05-17 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 21 | 12 | 2027-05-24 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 22 | 11 | 2027-05-31 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 23 | 12 | 2027-06-07 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 24 | 11 | 2027-06-14 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 25 | 11 | 2027-06-21 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027 | 26 | 2 | 2027-06-28 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027 | 16 | 2 | 2027-04-19 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027 | 17 | 1 | 2027-04-26 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027 | 26 | 2 | 2027-06-28 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027 | 15 | 2 | 2027-04-12 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027 | 18 | 4 | 2027-05-03 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027 | 19 | 1 | 2027-05-10 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027 | 20 | 2 | 2027-05-17 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028 | 45 | 3 | 2028-11-06 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028 | 46 | 3 | 2028-11-13 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028 | 50 | 4 | 2028-12-11 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 37 | 2 | 2028-09-11 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 44 | 1 | 2028-10-30 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 45 | 8 | 2028-11-06 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 46 | 7 | 2028-11-13 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 47 | 8 | 2028-11-20 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 48 | 7 | 2028-11-27 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 49 | 7 | 2028-12-04 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028 | 50 | 6 | 2028-12-11 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028 | 27 | 10 | 2028-07-03 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028 | 28 | 9 | 2028-07-10 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028 | 29 | 12 | 2028-07-17 | PLAN export 02-Sep-26
Formulas:
Week Starts (Mon) = IF(OR([ISO Year]="",[ISO Week]=""),"",DATE([ISO Year],1,4)-WEEKDAY(DATE([ISO Year],1,4),2)+1+([ISO Week]-1)*7)

## Release Log
RELEASE LOG — EVERY KIT RELEASED TO PRODUCTION
One line per release: date, contract, assy code, qty. Negative qty corrects a mistake. This is the only sheet updated day to day.
Example: 05-Oct-26 · E2A-R12P-T5-C · 92RRA00548AAA · 24 · N.Bakare · Rep 14
Date | Contract | Assy Code | Qty Released | Released By | Note (WO / repeater) | Description | Check | Row#
2026-04-20 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 1 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 6
2026-05-06 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 1 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 7
2026-05-06 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 1 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 8
2026-05-06 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 1 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 9
2026-05-14 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 1 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 10
2026-05-14 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 1 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 11
2026-05-14 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 12
2026-05-16 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 13
2026-05-18 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 1 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 14
2026-05-18 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 2 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 15
2026-05-18 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 2 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 16
2026-05-19 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 2 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 17
2026-05-20 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 2 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 18
2026-05-21 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 2 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 19
2026-05-21 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 2 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 20
2026-05-23 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 21
2026-05-23 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 22
2026-05-23 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 23
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 24
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 25
2026-05-28 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 2 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 26
2026-05-28 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 3 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 27
2026-05-28 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 3 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 28
2026-05-29 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 3 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 29
2026-06-03 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 1 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 30
2026-06-03 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 31
2026-06-03 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 32
2026-06-03 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 33
2026-06-04 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 1 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 34
2026-06-05 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 2 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 35
2026-06-07 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 2 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 36
2026-06-09 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 3 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 37
2026-06-09 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 3 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 38
2026-06-09 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 3 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 39
2026-06-15 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 4 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 40
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 41
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 42
2026-06-17 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 3 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 43
2026-07-20 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 3 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 44
2026-07-21 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 4 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 45
2026-07-22 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 5 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 46
2026-07-23 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 47
2026-07-23 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 48
2026-07-23 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 49
2026-07-23 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 3 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 50
2026-07-28 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 4 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 51
2026-07-28 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 4 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 52
2026-07-29 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 53
2026-07-31 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 4 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 54
2026-07-31 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 4 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 55
2026-08-04 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 4 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 56
2026-08-04 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 5 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 57
2026-08-04 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 5 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 58
2026-08-07 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 59
2026-08-07 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 60
2026-08-07 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 4 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 61
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 62
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 63
2026-08-08 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 4 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 64
2026-08-09 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 5 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 65
2026-08-09 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 6 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 66
2026-08-09 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 6 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 67
2026-08-10 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 5 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 68
2026-08-10 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 5 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 69
2026-08-10 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 6 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 70
2026-08-12 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 5 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 71
2026-08-12 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 72
2026-08-12 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 73
2026-08-12 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 74
2026-08-12 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 5 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 75
2026-08-17 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 6 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 76
2026-08-17 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 7 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 77
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 78
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 79
2026-08-18 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 5 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 80
2026-08-19 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 7 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 81
2026-08-22 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 6 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 82
2026-08-22 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 6 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 83
2026-08-22 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 6 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 84
2026-08-22 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 7 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 85
2026-08-25 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 8 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 86
2026-08-27 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 87
2026-08-27 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 88
2026-08-27 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 89
2026-08-27 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 6 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 90
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 91
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 92
2026-08-29 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 6 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 93
2026-09-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 7 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 94
2026-09-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 7 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 95
2026-09-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 8 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 96
2026-09-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 8 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 97
2026-09-04 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 7 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 98
2026-09-04 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 99
2026-09-04 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 100
2026-09-04 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 101
2026-09-04 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 7 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 102
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 103
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 104
2026-09-05 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 7 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 105
2026-09-07 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 7 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 106
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 9 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 107
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 10 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 108
2026-09-08 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 11 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 109
2026-09-09 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 110
2026-09-10 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 8 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 111
2026-09-11 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 8 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 112
2026-09-11 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 9 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 113
2026-09-11 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 12 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 114
2026-09-11 | E2A-R12P-T5-C | 91YAF03404AAA | 3 |  | Rep 13 (from COOIS) | R5B PSB SUB ASSEMBLY 4P-4FP |  | 115
2026-09-13 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 8 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 116
2026-09-13 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 8 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 117
2026-09-13 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 9 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 118
2026-09-16 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 119
2026-09-16 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 120
2026-09-16 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 8 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 121
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 122
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 123
2026-09-16 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 8 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 124
2026-09-16 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 125
2026-09-21 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 9 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 126
2026-09-21 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 10 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 127
2026-09-22 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 9 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 128
2026-09-22 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 9 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 129
2026-09-22 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 10 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 130
2026-09-28 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 9 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 131
2026-09-28 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 132
2026-09-28 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 133
2026-09-28 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 9 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 134
2026-09-28 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 135
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 136
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 137
2026-09-29 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 9 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 138
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 10 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 139
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 10 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 140
2026-10-01 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 10 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 141
2026-10-01 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 10 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 142
2026-10-01 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 143
2026-10-01 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 144
2026-10-01 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 10 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 145
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 146
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 147
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 10 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 148
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 11 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 149
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 11 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 150
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 11 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 151
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 11 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 152
2026-10-01 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 11 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 153
2026-10-01 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 11 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 154
2026-10-01 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 155
2026-10-01 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 156
2026-10-01 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 157
2026-10-01 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 11 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 158
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 159
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 160
2026-10-01 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 11 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 161
2026-10-01 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 12 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 162
2026-10-01 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 12 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 163
2026-10-01 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 164
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 12 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 165
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 12 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 166
2026-10-02 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 12 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 167
2026-10-02 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 12 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 168
2026-10-02 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 169
2026-10-02 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 170
2026-10-02 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 12 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 171
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 172
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 173
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 12 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 174
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BAA | 1 |  | Rep 13 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 1 - E2A |  | 175
2026-10-02 | E2A-R12P-T5-C | 92YLS00548BBA | 2 |  | Rep 13 (from COOIS) | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A |  | 176
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BAA | 1 |  | Rep 13 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A |  | 177
2026-10-02 | E2A-R12P-T5-C | 92YFD04548BBA | 2 |  | Rep 13 (from COOIS) | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A |  | 178
2026-10-02 | E2A-R12P-T5-C | 92YWS04548AAA | 3 |  | Rep 13 (from COOIS) | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A |  | 179
2026-10-02 | E2A-R12P-T5-C | 92RRA00548AAA | 24 |  | Rep 13 (from COOIS) | R5B ERBIUM SPOOL ASSEMBLY - E2A |  | 180
2026-10-02 | E2A-R12P-T5-C | 92YRA01548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 1 |  | 181
2026-10-02 | E2A-R12P-T5-C | 92YRA02548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 2 |  | 182
2026-10-02 | E2A-R12P-T5-C | 92YRA03548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 3 |  | 183
2026-10-02 | E2A-R12P-T5-C | 92YRA04548AAA | 3 |  | Rep 13 (from COOIS) | R5B ERBIUM ASSEMBLY POSITION 4 |  | 184
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BAA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 1 ASSY (4P-4FP) |  | 185
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BBA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 2 ASSY (4P-4FP) |  | 186
2026-10-02 | E2A-R12P-T5-C | 92UAP04548BCA | 1 |  | Rep 13 (from COOIS) | R5B BOAT 3 ASSY (4P-4FP) |  | 187

## How To Use
R5B AMP KITTING CONTROL — HOW IT WORKS
1. Update what has been kitted (every release)
Where | Sheet 'Release Log'. This is the ONLY sheet you touch day to day.
What to type | One line per assy code you release: Date · Contract (drop-down) · Assy Code (drop-down) · Qty Released · Released By · Note (e.g. 'Rep 14' or the WO number). Description and Check fill in by themselves.
Example — 1 repeater of E2A-R12P-T5-C | 14 lines, same date: 92YLS00548BAA 1 · 92YLS00548BBA 2 · 91YAF03404AAA 3 · 92YFD04548BAA 1 · 92YFD04548BBA 2 · 92YWS04548AAA 3 · 92RRA00548AAA 24 · 92YRA01548AAA 3 · 92YRA02548AAA 3 · 92YRA03548AAA 3 · 92YRA04548AAA 3 · 92UAP04548BAA 1 · 92UAP04548BBA 1 · 92UAP04548BCA 1. Tip: copy the 'To Release' column from the Dashboard.
Part release | Log only what actually went out (e.g. spool 16 of 24). The repeater counts once every code reaches a full set; the Dashboard 'Toward Next' column shows the part.
Mistake | Never delete. Add a correcting line with a negative qty (e.g. -3) and a note.
Check column | Red = something's wrong on that line (missing qty, code not on this contract's kit list, etc.).
2. Where the assembly codes go (once per contract)
Where | Sheet 'Kit Lists'. One row per assy code: Contract · Sequence (LASER ASSY, PSB ASSY, OPF ASSY, POB ASSY, ERBIUM ASSY, BOAT ASSY…) · Assy Code · Description · Qty per Repeater.
Where it comes from | ZMRP breakdown of the contract's top code (++). Qty per Repeater = how many of that code go into ONE repeater (e.g. spool 24).
Order | Rows show on the Dashboard in the order you type them, grouped by sequence. Keep each contract's rows together.
New contract | First add the contract on 'Contracts' (friendly name, project, top code ++, FP, amps per repeater, total repeaters), then its rows on 'Kit Lists', then its weeks on 'Weekly Plan'.
3. Kitted ahead of time
Just log it | Log the release with the real date you released it. The Dashboard compares kitted with the plan up to the 'As of' week: kitting early shows as AHEAD +n (green). Nothing else to change.
Plan moved | If the plan itself changes (CO41 dates move), edit the week/qty on 'Weekly Plan'. Kitting history stays untouched.
Planning the next batch | On the Dashboard, type the number of repeaters you want to reach in the pink 'Release Target' cell (e.g. management asks for 2 more: kitted + 2). 'To Release' shows exactly what to release per code.
4. Reading the Dashboard
Repeaters kitted | Per code: released ÷ qty per repeater (rounded down). Contract figure = the LOWEST code, because a repeater needs every code. The limiting code is highlighted red.
Amps kitted | Repeaters kitted × amps per repeater (= FP).
Plan to date / Vs plan | 'Weekly Plan' weeks are FINAL BUILD (housing) weeks. Kits are due 'Kit Lead' weeks earlier (Contracts, default 2: kit W−2, AMPS build W−1, housing W). Plan to date = repeaters whose housing week is up to 'As of' + lead. Vs plan = kitted − plan to date.
Gantt | Sheet 'Gantt': ISO weeks across, three rows per contract — Kit release (W−2), AMPS build (W−1), Final build / housing (W) — with the repeater numbers in each week. Kit cells turn green once kitted, red if overdue. Change the start week in the pink cell.
Contract total changes | Change 'Total Repeaters' on 'Contracts' (e.g. 109 → 117). Everything recalculates.
Why it stays fast | No SAP dumps. Only your plan numbers and release lines — a few hundred rows per contract.

## Calc (hidden)
Helper sheet for the Dashboard chart and table — do not edit. |  |  | 2026-07-13
|  |  | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12
Slot | Code | Qty/Rep
1 | 92YLS00548BAA | 1 | 3 | 3 | 4 | 6 | 6 | 7 | 7 | 8 | 9 | 9 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
2 | 92YLS00548BBA | 2 | 3 | 3 | 4 | 5 | 5 | 6 | 6 | 7 | 8 | 8 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
3 | 91YAF03404AAA | 3 | 4 | 5 | 5 | 6 | 6 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
4 | 92YFD04548BAA | 1 | 3 | 3 | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 9 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
5 | 92YFD04548BBA | 2 | 3 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 8 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
6 | 92YWS04548AAA | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 8 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
7 | 92RRA00548AAA | 24 | 2 | 3 | 3 | 4 | 5 | 6 | 6 | 6 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
8 | 92YRA01548AAA | 3 | 2 | 3 | 3 | 4 | 5 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
9 | 92YRA02548AAA | 3 | 2 | 3 | 3 | 4 | 5 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
10 | 92YRA03548AAA | 3 | 2 | 3 | 4 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
11 | 92YRA04548AAA | 3 | 2 | 3 | 3 | 4 | 5 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
12 | 92UAP04548BAA | 1 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
13 | 92UAP04548BBA | 1 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
14 | 92UAP04548BCA | 1 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
15
16
17
18
19
20
|  | Week | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15
|  | Kit plan (cumulative) | 8 | 10 | 12 | 14 | 17 | 19 | 19 | 20 | 22 | 24 | 26 | 28 | 31 | 32 | 33 | 33 | 33 | 33 | 33 | 35 | 35 | 35 | 35 | 44 | 46 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 53 | 54
|  | Kitted (flat after today) | 2 | 3 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  | Contract total | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109

## GanttCalc (hidden)
Helper for Gantt — do not edit
Week start | time axis 2026-08-17 to 2027-08-30
WKE-R24P-T1-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 12 | 15 | 19 | 23 | 27 | 32 | 36 | 40 | 45 | 49 | 52 | 56 | 60 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 68 | 74 | 81 | 88 | 95 | 102 | 109 | 116 | 124 | 131
WBA-R24P-T1-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E2A-R4P-T1-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 11 | 12 | 20 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
E2A-R4P-T2-M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 8 | 8 | 8 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
E2A-R6P-T3-M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
E2A-R8P-T4-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
E2A-R12P-T5-C | 14 | 17 | 19 | 19 | 20 | 22 | 24 | 26 | 28 | 31 | 32 | 33 | 33 | 33 | 33 | 33 | 35 | 35 | 35 | 35 | 44 | 46 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 53 | 54 | 55 | 60 | 67 | 79 | 90 | 102 | 113 | 124 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126
E2A-R12P-T6-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
E2A-R16P-T7-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
DARAJA-R8P (TBC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DARAJA-R24P (TBC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REUNION-SOUTH-R16P (TBC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0