## Dashboard
0
R5B E2A 12FP COLD T5 · REPEATER COUNTER | [6 empty] | REPEATERS REQUESTED ▸ | 2
Contract R5B · E2A 12FP Cold T5 · 92ERP12548A++ · 12FP · Contract: 13 repeaters · 0 releases logged | [7 empty] | type the target here
REPEATERS KITTED |  | REQUEST STATUS | UNITS TO RELEASE |  |  | CONTRACT PROGRESS
0 |  | 2 TO GO | 102 |  |  | 0%
of 13 in contract · counts when all 14 codes are released |  | target 2 repeaters · 0 of 14 codes ready | to reach the requested repeaters |  |  | 0 of 13 repeaters kitted
REPEATER COUNTER
Sequence | Assy Code | Description | Qty / Rep | Released | Repeaters | Needed for Request | To Release Now | Status | Repeater
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 0 | 0 | 2 | 2 | RELEASE 2 | Rep 1 · —
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 0 | 0 | 4 | 4 | RELEASE 4 | Rep 2 · —
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 3 · —
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 0 | 0 | 2 | 2 | RELEASE 2 | Rep 4 · —
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 0 | 0 | 4 | 4 | RELEASE 4 | Rep 5 · —
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 6 · —
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 0 | 0 | 48 | 48 | RELEASE 48 | Rep 7 · —
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 8 · —
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 9 · —
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 10 · —
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 0 | 0 | 6 | 6 | RELEASE 6 | Rep 11 · —
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 0 | 0 | 2 | 2 | RELEASE 2 | Rep 12 · —
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 0 | 0 | 2 | 2 | RELEASE 2 | Rep 13 · —
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 0 | 0 | 2 | 2 | RELEASE 2
| TOTAL | Repeaters column total = lowest code (highlighted) — that code limits the count |  | 0 | 0 | 102 | 102
LATEST RELEASES
Date | Assy Code | Description | Qty | Released By | Logged | Note

## Contract
CONTRACT — WHAT ONE REPEATER NEEDS
Blue cells are inputs. Change these only when the contract or kitting plan changes.
Contract | R5B
Program | E2A 12FP Cold T5
ERP item | 92ERP12548A++
Config | 12FP
Contract repeaters | 13
Already released before this log started (leave 0 to start fresh)
Sequence | Assy Code | Assy Description | Qty per Repeater | Opening Balance | Contract Qty
LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 0 | 13
LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 0 | 26
PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 0 | 39
OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 0 | 13
OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 0 | 26
POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 0 | 39
ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 0 | 312
ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 0 | 39
ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 0 | 39
ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 0 | 39
ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 0 | 39
BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 0 | 13
BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 0 | 13
BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 0 | 13

## Release Log
RELEASE LOG
One line per release to production. Type the date, pick the assy code, enter the qty released. The Dashboard counts repeaters from this.
Example: 03-Oct-26 · 92RRA00548AAA · 24 · N.Bakare · for Rep 14
Date | Assy Code | Description | Qty Released | Released By | Note (WO / repeater) | Check

## How To Use
HOW THE REPEATER COUNTER WORKS
Each time management asks
1. Set the target | Type the number of repeaters requested in the pink cell on the Dashboard (top right).
2. Release | The 'To Release Now' column tells you how many of each assy code to release to reach the target. Release those work orders and send them to production.
3. Log it | On 'Release Log' add one line per release: date, assy code (drop-down), qty released, your name, optional note (WO no. / repeater). Made a mistake? Add a line with a negative qty.
4. Everyone sees it | The Dashboard updates immediately: Repeaters Kitted, the counter, and Latest Releases. Save the file on SharePoint / Teams so everyone sees the same numbers.
How it counts
Repeaters per code | Released qty ÷ qty per repeater, rounded down. E.g. erbium spool: 50 released ÷ 24 = 2 repeaters (2 units toward the 3rd).
Repeaters kitted | The lowest value across all assy codes — a repeater only counts when every code has been released for it. The limiting code is highlighted in the table.
Starting point | If some repeaters were released before you started the log, put those quantities in 'Opening Balance' on the Contract sheet.
Changing the contract | Edit codes, qty per repeater or contract repeaters on the Contract sheet (blue cells). Everything follows.
Projecting | Open the Dashboard and press Ctrl+F1 to hide the ribbon. It fits one landscape screen.