## Start Here
R5B AMP KITTING CONTROL — START HERE
Microsoft 365 workbook. No macros, no external connections. Yellow = you type. Grey = calculated, do not type.
EVERY WEEK — UPDATE SUPPLIED TOTALS
Where | 'Assemblies & Totals'. Find the row for the contract and assembly code.
Rule | Enter the TOTAL supplied to date, not this week's additions. If the existing total is 26 and another 4 are supplied, enter 30.
Then fill | Updated on (date) · Updated by (your name) · Source reference (e.g. the SAP export filename you checked).
Worked example | Spool 92RRA00548AAA shows 312. This week 24 more were supplied. Type 336 in 'Cumulative supplied to date', today's date in 'Updated on', your name, and e.g. 'COOIS_E2A_2026-10-12.xlsx'.
Correcting a mistake | Type the correct total (it may be lower) and write why in 'Correction note', e.g. '-3: duplicate WO counted on 05-Oct'. The workbook does not keep old values, so the note is the record.
READING THE DASHBOARD
Pick a contract | Yellow cell at the top of 'Dashboard'. The list grows automatically when contracts are added.
Complete repeater kits released | One complete repeater kit means every required assembly has been supplied. It does not mean the repeater has finished production. It is the LOWEST number of complete sets across the contract's assemblies; the limiting row is red in the list.
Kits due by this week | Repeaters whose kit-release week (final build week minus the kit lead) is this week or earlier. Compared with current plan, not the original commitment.
Ahead / behind current plan | Complete kits minus kits due by this week.
Kits due over the next four weeks | Repeaters whose kit-release week falls in the next four weeks.
Target | Yellow cell. Blank = kits due by this week + next four weeks. Type a number to plan a specific batch. 'Additional needed' = max(0, target × qty per repeater − supplied).
Supplied totals line | Shows the latest and oldest update dates, mixed dates, missing dates, and OUT OF DATE when the oldest is older than the interval on 'Contracts' (cell C4).
Next action | One concrete step taken from the data (setup → update totals → shortage → covered). It never states production status, availability or completion dates.
Gantt | Pick a contract. Weekly quantities for kit release, AMPS build and final build (scheduled). Red line = this week. 'Kit coverage' compares cumulative kits due with current complete kits. Plan rows outside the 52-week view are counted above the grid.
CONTRACT SETUP (once per contract)
1. Contracts | Add a row: unique Contract ID, friendly name, project, top-level ++ code, amps per repeater, total repeaters required, kit-release lead (default 2), AMPS-build lead (default 1), plan revision/date/updater, notes.
2. Assemblies & Totals | One row per required assembly code from the ZMRP breakdown: contract, group (LASER ASSY…), code, description, qty per repeater, cumulative supplied (0 if none), update details. The same code in two contracts = two rows.
3. Weekly Plan | One row per final build week: contract, Monday date, repeaters planned.
Checks | Each input sheet has a Check column. Anything other than OK needs fixing. 'Assembly setup required' = no assemblies yet.
PLAN MAINTENANCE
Move a batch | Change the Monday date on its row.
Change quantity | Change 'Repeaters planned'.
Split | Reduce the quantity on the row and add a new row for the other week.
Cancel | Delete the row (or set the quantity to 0).
Replace a contract's whole plan | Filter 'Contract' on 'Weekly Plan', select and delete ALL of that contract's rows (right-click → Delete → Table Rows), clear the filter, paste the new rows at the bottom of the table. Do not keep old and new rows together. Update Plan revision / updated on / updated by on 'Contracts'. Other contracts are not affected.
Dates | Always the MONDAY of the final build (housing) week. ISO week labels are calculated, so year boundaries (W52/W53 → W01) work automatically.
SOURCES, FILES AND BACKUPS
Verified supplied totals | Production controller / kitting lead, from SAP (COOIS for released orders, CO41 for release dates, ZMRP for the assembly breakdown). Record the export filename in 'Source reference'.
Plan | Production planning (PLAN / ASP export). Record its name in 'Plan revision' on 'Contracts'.
SAP exports | Keep full exports in the company folder for SAP exports — never paste them into this workbook (it keeps it fast).
History archive | 'R5B-AMP-Release-Log-Archive.xlsx' holds the old Release Log (182 lines) and the migration reconciliation. It is read-only history; this workbook does not use it.
Backups | Save a dated copy before replacing a plan or doing large updates (e.g. R5B-AMP-Kitting-Control_2026-10-05.xlsx) in the team backup folder.
Why no import | A this-week-only SAP export cannot give the cumulative total without a verified opening balance, so totals are typed from a verified cumulative figure.
IF A FORMULA IS OVERWRITTEN
Grey table columns | Copy a grey cell from the row above and paste it into the broken cell; or type the formula once in any cell of the column and Excel refills the whole column. Formulas are listed below.
Complete sets (calc) | Type: =IF(AND(ISNUMBER([@[Qty per repeater]]),[@[Qty per repeater]]>0,[@[Qty per repeater]]=INT([@[Qty per repeater]])),INT(IF(ISNUMBER([@[Cumulative supplied to date]]),[@[Cumulative supplied to date]],0)/[@[Qty per repeater]]),"")
Check columns | Copy from the row above (same table).
ISO week (calc) | Type: =IF(ISNUMBER([@[Final build week (Monday)]]),"W"&TEXT(ISOWEEKNUM([@[Final build week (Monday)]]),"00")&"-"&YEAR([@[Final build week (Monday)]]-WEEKDAY([@[Final build week (Monday)]],2)+4),"")
Dashboard / Gantt | These sheets are protected (no password) so formulas cannot be overwritten by accident. Review → Unprotect Sheet only for maintenance, then protect again.

## Dashboard
Kits (number or message)
R5B AMP KITTING CONTROL | [10 empty] | Total required
CONTRACT ▸ | E2A-R12P-T5-C | [9 empty] | Kit lead (weeks)
AMPS lead (weeks)
One complete repeater kit means every required assembly has been supplied. It does not mean the repeater has finished production. | [10 empty] | Kits due by this week
Kits due next 4 weeks
COMPLETE REPEATER KITS RELEASED |  | KITS DUE BY THIS WEEK | AHEAD / BEHIND CURRENT PLAN |  |  | KITS DUE OVER THE NEXT FOUR WEEKS |  | ADDITIONAL ASSEMBLIES NEEDED TO REACH TARGET |  |  | Scheduled total
Target in use
Assemblies count
Setup issues (qty/dup/unknown)
PROGRESS | [10 empty] | Assemblies without update date
SCHEDULE CHECK | [10 empty] | Latest update
PLAN REVISION | [10 empty] | Oldest update
SUPPLIED TOTALS | [10 empty] | Supplied totals missing
SETUP | [10 empty] | Additional assemblies needed
NEXT ACTION | [10 empty] | Codes short
Largest gap
TARGET | Target complete repeater kits (type a number, or leave blank to use kits due by this week + next 4 weeks) ▸ | [9 empty] | Age of oldest update (days)
REQUIRED ASSEMBLIES (actual cumulative supplied totals) | [5 empty] | Needed / Additional use the target above |  |  |  |  | Next kit-release week (Monday)
Assembly group | Assembly code | Description | Qty per repeater | Supplied to date | Complete sets | Toward next set | Needed for target | Additional needed | Updated on | Check | Repeaters in that week

## Gantt
R5B AMP KITTING — WEEKLY SCHEDULE
CONTRACT ▸ | E2A-R12P-T5-C
Weeks before this week ▸ | 6
…or fixed start date ▸ |  | window start | Kit release, AMPS build and final build show SCHEDULED quantities from the Weekly Plan. Supplied totals show how many kits are covered, not which weekly batch was released, and say nothing about AMPS-build or final-build completion.
|  |  | Kit release (scheduled) | Kit covered by supplied totals | Kit due, NOT covered | AMPS build (scheduled) | Final build / housing (scheduled) | │ red line = this week
ISO year
ISO week
Week starts (Mon)
in view
Kit release | W − kit lead
AMPS build | W − AMPS lead
Final build / housing | W (plan week)
Cumulative kits due | end of each kit week | kits ▸
Kit coverage | vs current supplied totals
Complete kits supplied now
Formulas:
Kit release (scheduled) = "W"&TEXT(ISOWEEKNUM([Kit release (scheduled), row below]),"00")
Kit covered by supplied totals = "W"&TEXT(ISOWEEKNUM([Kit covered by supplied totals, row below]),"00")
Kit due, NOT covered = "W"&TEXT(ISOWEEKNUM([Kit due, NOT covered, row below]),"00")
AMPS build (scheduled) = "W"&TEXT(ISOWEEKNUM([AMPS build (scheduled), row below]),"00")
Final build / housing (scheduled) = "W"&TEXT(ISOWEEKNUM([Final build / housing (scheduled), row below]),"00")

## Contracts
CONTRACTS
One row per contract (top-level ++ code). Yellow columns are typed; grey columns calculate. New rows appear automatically in the Dashboard and Gantt contract lists.
SETTING – Update interval (days) |  | 7 | Supplied totals older than this are flagged as out of date on the Dashboard.
INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | CALCULATED – do not type ▼
Contract ID | Friendly name | Project | Top-level assembly code | Amps per repeater | Total repeaters required | Kit-release lead (weeks before final build) | AMPS-build lead (weeks before final build) | Plan revision | Plan updated on | Plan updated by | Notes | Setup check
WKE-R24P-T1-C | Wamkelekile · 24FP | Wamkelekile | 92ERP24543A++ | 24 | 255 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
WBA-R24P-T1-C | Waban · 24FP | Waban | 92ERP24545A++ | 24 | 200 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R4P-T1-C | E2A · 4FP | E2A | 92ERP04548A++ | 4 | 39 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R4P-T2-M | E2A · 4FP | E2A | 92ERP04548B++ | 4 | 11 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R6P-T3-M | E2A · 6FP | E2A | 92ERP06548A++ | 6 | 3 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R8P-T4-C | E2A · 8FP | E2A | 92ERP08548A++ | 8 | 10 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R12P-T5-C | E2A · 12FP | E2A | 92ERP12548A++ | 12 | 109 | 2 | 1 | PLAN export 02-Sep-26 + ASP 01 2026 (Jan-26) weeks W24–W35 | 2026-10-05 | Migrated from previous workbook
E2A-R12P-T6-C | E2A · 12FP | E2A | 92ERP12548B++ | 12 | 5 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
E2A-R16P-T7-C | E2A · 16FP | E2A | 92ERP16548A++ | 16 | 9 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook
DARAJA-R8P (TBC) | Daraja Ext to SA · 8FP (TBC) | Daraja Ext to SA | Not yet released | 8 | 10 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook | Top code not yet released
DARAJA-R24P (TBC) | Daraja Ext to SA · 24FP (TBC) | Daraja Ext to SA | Not yet released | 24 | 46 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook | Top code not yet released
REUNION-SOUTH-R16P (TBC) | Reunion-South Africa (wet plant only) · 16FP (TBC) | Reunion-South Africa (wet plant only) | Not yet released | 16 | 31 | 2 | 1 | PLAN export 02-Sep-26 | 2026-10-05 | Migrated from previous workbook | Top code not yet released

## Assemblies & Totals
ASSEMBLIES & TOTALS
Enter the TOTAL supplied to date, not this week's additions. If the existing total is 26 and another 4 are supplied, enter 30.
When you change a total, also update 'Updated on', 'Updated by' and 'Source reference' (e.g. the SAP export filename). If you REDUCE a total to correct a mistake, write why in 'Correction note'. The workbook does not keep previous values.
One row per contract + assembly code. A code used by two contracts needs two rows (separate totals).
INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | CALCULATED – do not type ▼ | CALCULATED – do not type ▼
Contract | Assembly group | Assembly code | Description | Qty per repeater | Cumulative supplied to date | Updated on | Updated by | Source reference | Correction note | Complete sets (calc) | Check (calc)
E2A-R12P-T5-C | LASER ASSY | 92YLS00548BAA | R5B LASER ASSEMBLY 4P BOAT 1 - E2A | 1 | 13 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | LASER ASSY | 92YLS00548BBA | R5B LASER ASSEMBLY 4P BOAT 2/3 - E2A | 2 | 26 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 3 | 39 | 2026-09-11 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | OPF ASSY | 92YFD04548BAA | R5B OPF ASSEMBLY (4P-4FP) BOAT 1 - E2A | 1 | 13 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | OPF ASSY | 92YFD04548BBA | R5B OPF ASSEMBLY (4P-4FP) BOAT 2/3 - E2A | 2 | 26 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | POB ASSY | 92YWS04548AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - E2A | 3 | 39 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | ERBIUM ASSY | 92RRA00548AAA | R5B ERBIUM SPOOL ASSEMBLY - E2A | 24 | 312 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA01548AAA | R5B ERBIUM ASSEMBLY POSITION 1 | 3 | 39 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA02548AAA | R5B ERBIUM ASSEMBLY POSITION 2 | 3 | 39 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA03548AAA | R5B ERBIUM ASSEMBLY POSITION 3 | 3 | 39 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | ERBIUM ASSY | 92YRA04548AAA | R5B ERBIUM ASSEMBLY POSITION 4 | 3 | 39 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BAA | R5B BOAT 1 ASSY (4P-4FP) | 1 | 13 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BBA | R5B BOAT 2 ASSY (4P-4FP) | 1 | 13 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
E2A-R12P-T5-C | BOAT ASSY | 92UAP04548BCA | R5B BOAT 3 ASSY (4P-4FP) | 1 | 13 | 2026-10-02 | Migrated from previous workbook | Previous workbook Release Log (182 lines from COOIS new_e2a, 03-Oct-26)
WKE-R24P-T1-C | LASER ASSY | 92YLS00543AAA | R5B LASER ASSEMBLY 4P-4P BOAT 1 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | LASER ASSY | 92YLS00543ABA | R5B LASER ASSEMBLY 4P-4P BOAT 2 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | LASER ASSY | 92YLS00543ACA | R5B LASER ASSEMBLY 4P-4P BOAT 3 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | PSB ASSY | 91YAF03404AAA | R5B PSB SUB ASSEMBLY 4P-4FP | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | OPF ASSY | 92YFD44543AAA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 1 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | OPF ASSY | 92YFD44543ABA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 2 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | OPF ASSY | 92YFD44543ACA | R5B OPF ASSEMBLY 2X(4P-4FP) BOAT 3 - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | POB ASSY | 92YWS04543AAA | R5B 4FP POB LUMENTUM SUB ASSEMBLY - WKE | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA01543AAA | R5B ERBIUM ASSEMBLY 1 - WKE | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA02543AAA | R5B ERBIUM ASSEMBLY 2 - WKE | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA03543AAA | R5B ERBIUM ASSEMBLY 3 - WKE | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | ERBIUM ASSY | 92YRA04543AAA | R5B ERBIUM ASSEMBLY 4 - WKE | 6 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | ERBIUM ASSY | 92RRA00543AAA | R5B ERBIUM SPOOL ASSEMBLY - WKE | 48 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543AAA | R5B BOAT 1 ASSY 2X(4P-4FP) L - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543ABA | R5B BOAT 2 ASSY 2X(4P-4FP) L - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded
WKE-R24P-T1-C | BOAT ASSY | 92UAP44543ACA | R5B BOAT 3 ASSY 2X(4P-4FP) L - WKE | 1 | 0 |  |  | Previous workbook: no releases recorded

## Weekly Plan
WEEKLY PLAN — FINAL BUILD / HOUSING WEEKS
Each row = repeaters planned for FINAL BUILD (housing) in the week starting on that Monday. Kit release and AMPS build weeks are calculated from the lead times on 'Contracts'.
Move: change the date · Split: change the qty and add a row · Cancel: delete the row (or set qty 0) · Replace a whole schedule: filter Contract, delete ALL its rows, then paste the new rows. Never leave old and new rows together. Record the new plan revision on 'Contracts'.
INPUT ▼ | INPUT ▼ | INPUT ▼ | INPUT ▼ | CALCULATED – do not type ▼ | CALCULATED – do not type ▼
Contract | Final build week (Monday) | Repeaters planned | Note | ISO week (calc) | Check (calc)
WKE-R24P-T1-C | 2026-10-26 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026-11-02 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026-11-09 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026-11-16 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026-11-23 | 2 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2026-11-30 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-01-25 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-02-01 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-02-08 | 3 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-02-15 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-02-22 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-03-01 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-03-08 | 5 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-03-15 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-03-22 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-03-29 | 5 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-04-05 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-04-12 | 3 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-04-19 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-04-26 | 4 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-05-03 | 2 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-05-10 | 1 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-06-28 | 5 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-07-05 | 6 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-07-12 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-07-19 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-07-26 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-08-02 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-08-09 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-08-16 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-08-23 | 8 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-08-30 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-09-06 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-09-13 | 6 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-09-20 | 8 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-09-27 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-10-04 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-10-11 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-10-18 | 5 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-10-25 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-11-01 | 8 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-11-08 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-11-15 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-11-22 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-11-29 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-12-06 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-12-13 | 8 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2027-12-20 | 7 | PLAN export 02-Sep-26
WKE-R24P-T1-C | 2028-01-10 | 12 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2027-10-18 | 2 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-01-10 | 1 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-01-24 | 8 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-01-31 | 7 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-02-07 | 7 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-02-14 | 8 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-02-21 | 8 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-02-28 | 8 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-03-06 | 8 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-03-13 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-03-20 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-03-27 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-04-03 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-04-10 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-04-17 | 3 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-04-24 | 2 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-05-01 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-05-08 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-05-15 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-05-22 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-05-29 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-06-05 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-06-12 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-06-19 | 9 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-06-26 | 10 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-07-03 | 3 | PLAN export 02-Sep-26
WBA-R24P-T1-C | 2028-07-10 | 3 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026-11-09 | 5 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026-11-16 | 6 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026-11-23 | 1 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026-11-30 | 8 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2026-12-07 | 8 | PLAN export 02-Sep-26
E2A-R4P-T1-C | 2027-01-25 | 11 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-04-19 | 1 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-05-03 | 2 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-05-10 | 5 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-06-07 | 1 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-06-14 | 1 | PLAN export 02-Sep-26
E2A-R4P-T2-M | 2027-06-21 | 1 | PLAN export 02-Sep-26
E2A-R6P-T3-M | 2027-03-22 | 3 | PLAN export 02-Sep-26
E2A-R8P-T4-C | 2026-12-14 | 8 | PLAN export 02-Sep-26
E2A-R8P-T4-C | 2027-01-04 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-06-08 | 1 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-06-29 | 1 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-07-06 | 1 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-07-13 | 1 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-07-20 | 2 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-07-27 | 2 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-08-03 | 2 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-08-10 | 2 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-08-17 | 2 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-08-24 | 3 | ASP 01 2026 (Jan-26 view) — weeks before W36
E2A-R12P-T5-C | 2026-08-31 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-09-14 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-09-21 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-09-28 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-10-05 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-10-12 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-10-19 | 3 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-10-26 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-11-02 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2026-12-07 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-01-04 | 9 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-01-11 | 2 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-01-18 | 6 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-04-19 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-04-26 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-05-03 | 1 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-05-10 | 5 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-05-17 | 7 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-05-24 | 12 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-05-31 | 11 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-06-07 | 12 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-06-14 | 11 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-06-21 | 11 | PLAN export 02-Sep-26
E2A-R12P-T5-C | 2027-06-28 | 2 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027-04-19 | 2 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027-04-26 | 1 | PLAN export 02-Sep-26
E2A-R12P-T6-C | 2027-06-28 | 2 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027-04-12 | 2 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027-05-03 | 4 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027-05-10 | 1 | PLAN export 02-Sep-26
E2A-R16P-T7-C | 2027-05-17 | 2 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028-11-06 | 3 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028-11-13 | 3 | PLAN export 02-Sep-26
DARAJA-R8P (TBC) | 2028-12-11 | 4 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-09-11 | 2 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-10-30 | 1 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-11-06 | 8 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-11-13 | 7 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-11-20 | 8 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-11-27 | 7 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-12-04 | 7 | PLAN export 02-Sep-26
DARAJA-R24P (TBC) | 2028-12-11 | 6 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028-07-03 | 10 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028-07-10 | 9 | PLAN export 02-Sep-26
REUNION-SOUTH-R16P (TBC) | 2028-07-17 | 12 | PLAN export 02-Sep-26